## Report
Test Project | [16 empty] | [Company Name / Logo]
Earned Value Analysis Report
Earned Value Management Template
| Prepared By: | Daffa M Azhar | [15 empty] | © 2012 Vertex42 LLC
| Date: | 4 Oktober 2021
[42]
| For Period: | Week 7
Summary:
Laporan keuangan projek SI RBTC pada minggu ke-7 pengerjaan.
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | ← You can change the labels for the periods (e.g. Week 1/2/3, Jan/Feb/Mar, etc.)
1.1 | Penyusunan Staff | 275000 | 275000 | [14 empty] | ← Enter or edit values in the light-blue cells.
1.2 | Pembuatan Project Charter | 1135200 | 1135200
2.1 | Manajemen Integrasi | 3575000 | 825000 | 1375000 | 1375000
2.2 | Manajemen Ruang Lingkup | 550000 | 550000
2.3 | Manajeman Waktu | 825000 | 275000 | 550000
2.4 | Manajemen Biaya | 550000 | 275000 | 275000
2.5 | Manajemen Kualitas | 275000 |  | 275000
2.6 | Manajemen Sumber Daya | 550000 |  | 550000
2.7 | Manajemen Komunikasi | 550000 |  | 550000
2.8 | Manajemen Risiko | 825000 |  |  | 825000
2.9 | Manajemen Pengadaan | 550000 |  |  | 550000
3.1 | Perencanaan dan Analisis | 1750000 |  |  |  | 1750000
3.2 | Desain | 26823041 |  |  |  | 5043041 | 14720000 | 7060000
3.3 | Implementasi | 5880000 | [5 empty] | 630000 | 1050000 | 1050000 | 1050000 | 1050000 | 1050000
3.4 | Testing dan Deployment | 10320000 | [11 empty] | 9270000 | 1050000
3.5 | Maintenance | 2940000 | [13 empty] | 2100000 | 840000
4.1 | Integrated Control | 0
4.2 | Kontrol Ruang Lingkup | 0
4.3 | Kontrol Waktu | 0
4.4 | Kontrol Biaya | 0
4.5 | Kontrol Kualitas | 0
4.6 | Kontrol Komunikasi | 0
4.7 | Kontrol Risiko | 0
4.8 | Kontrol Pengadaan | 0
5.1 | Penutupan Proyek | 275000 | [14 empty] | 275000
5.2 | Penutupan Pengadaan | 275000 | [14 empty] | 275000
Insert new rows above this one | [17 empty] | ← To add more tasks, insert rows above this one. You can or delete this row after you are done adding tasks.
| Total Budgeted Cost | 57923241 | 3335200 | 3575000 | 2750000 | 6793041 | 14720000 | 7690000 | 1050000 | 1050000 | 1050000 | 1050000 | 1050000 | 9270000 | 1050000 | 2100000 | 1390000
|  | Cumulative Planned Value (PV) | 3335200 | 6910200 | 9660200 | 16453241 | 31173241 | 38863241 | 39913241 | 40963241 | 42013241 | 43063241 | 44113241 | 53383241 | 54433241 | 56533241 | 57923241
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 3335200 | 6910200 | 9660200 | 16453241 | 31173241 | 38863241 | 39913241 | 40963241 | 41593241 | 41593241 | 41593241 | 41593241 | 41593241 | 41593241 | #REF! | ← Enter the Actual Costs as calculated from the AC worksheet.
|  | Cumulative Earned Value (EV) | 4435200 | 7212700 | 9660200 | 22139416.4 | 30186328.7 | 39409241 | 39997241 | [7 empty] | #REF! | ← Enter the Earned Value as calculated from the EV worksheet.
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | 1100000 | 302500 | 0 | 5686175.4 | -986912.3 | 546000 | 84000 | - | - | - | - | - | - | - | #REF!
|  | Schedule Variance (SV = EV - PV) | 1100000 | 302500 | 0 | 5686175.4 | -986912.3 | 546000 | 84000 | - | - | - | - | - | - | - | #REF!
|  | Cost Performance Index (CPI = EV/AC) | 1.3298 | 1.0438 | 1 | 1.3456 | 0.96834 | 1.014 | 1.0021 | - | - | - | - | - | - | - | #REF!
|  | Schedule Performance Index (SPI = EV/PV) | 1.3298 | 1.0438 | 1 | 1.3456 | 0.96834 | 1.014 | 1.0021 | - | - | - | - | - | - | - | #REF!
|  | Estimated Cost at Completion (EAC) | 43557357.82 | 55493945.4 | 57923241 | 43046529.61 | 59816984.34 | 57120736.59 | 57801593.8 | - | - | - | - | - | - | - | #REF!

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15
1.1 | Penyusunan Staff | 275000 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
1.2 | Pembuatan Project Charter | 1135200 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.1 | Manajemen Integrasi | 3575000 | 50% | 70% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.2 | Manajemen Ruang Lingkup | 550000 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.3 | Manajeman Waktu | 825000 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.4 | Manajemen Biaya | 550000 | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.5 | Manajemen Kualitas | 275000 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.6 | Manajemen Sumber Daya | 550000 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.7 | Manajemen Komunikasi | 550000 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.8 | Manajemen Risiko | 825000 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2.9 | Manajemen Pengadaan | 550000 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3.1 | Perencanaan dan Analisis | 1750000 |  |  |  | 100% | 100% | 100% | 100% | 100% | 100%
3.2 | Desain | 26823041 |  |  |  | 40% | 70% | 100% | 100% | 100% | 100%
3.3 | Implementasi | 5880000 | [5 empty] | 20% | 30% | 40% | 50%
3.4 | Testing dan Deployment | 10320000
3.5 | Maintenance | 2940000
4.1 | Integrated Control | 0
4.2 | Kontrol Ruang Lingkup | 0
4.3 | Kontrol Waktu | 0
4.4 | Kontrol Biaya | 0
4.5 | Kontrol Kualitas | 0
4.6 | Kontrol Komunikasi | 0
4.7 | Kontrol Risiko | 0
4.8 | Kontrol Pengadaan | 0
5.1 | Penutupan Proyek | 275000
5.2 | Penutupan Pengadaan | 275000
Insert new rows above this one
|  | Cumulative EV | 4435200 | 7212700 | 9660200 | 22139416.4 | 30186328.7 | 39409241 | 39997241

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15
1.1 | Penyusunan Staff |  | Wk 1: 275000
1.2 | Pembuatan Project Charter |  | Wk 1: 1135200
2.1 | Manajemen Integrasi |  | Wk 1: 825000; Wk 2: 1375000; Wk 3: 1375000
2.2 | Manajemen Ruang Lingkup |  | Wk 1: 550000
2.3 | Manajeman Waktu |  | Wk 1: 275000; Wk 2: 550000
2.4 | Manajemen Biaya |  | Wk 1: 275000; Wk 2: 275000
2.5 | Manajemen Kualitas |  | Wk 2: 275000
2.6 | Manajemen Sumber Daya |  | Wk 2: 550000
2.7 | Manajemen Komunikasi |  | Wk 2: 550000
2.8 | Manajemen Risiko |  | Wk 3: 825000
2.9 | Manajemen Pengadaan |  | Wk 3: 550000
3.1 | Perencanaan dan Analisis |  | Wk 4: 1750000
3.2 | Desain |  | Wk 4: 5043041; Wk 5: 14720000; Wk 6: 7060000
3.3 | Implementasi |  | Wk 6: 630000; Wk 7: 1050000; Wk 8: 1050000; Wk 9: 630000
3.4 | Testing dan Deployment | bar: Wk 12 to Wk 13
3.5 | Maintenance | bar: Wk 14 to Wk 15
4.1 | Integrated Control | bar: Wk 4 to Wk 15
4.2 | Kontrol Ruang Lingkup | bar: Wk 6 to Wk 8
4.3 | Kontrol Waktu | bar: Wk 8 to Wk 15
4.4 | Kontrol Biaya | bar: Wk 14
4.5 | Kontrol Kualitas | bar: Wk 14
4.6 | Kontrol Komunikasi | bar: Wk 4 to Wk 15
4.7 | Kontrol Risiko | bar: Wk 12 to Wk 13
4.8 | Kontrol Pengadaan | bar: Wk 13 to Wk 14
5.1 | Penutupan Proyek | bar: Wk 15
5.2 | Penutupan Pengadaan | bar: Wk 15
Insert new rows above this one
|  | Total Actual Cost | 3335200 | 3575000 | 2750000 | 6793041 | 14720000 | 7690000 | 1050000 | 1050000 | 630000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 3335200 | 6910200 | 9660200 | 16453241 | 31173241 | 38863241 | 39913241 | 40963241 | 41593241 | 41593241 | 41593241 | 41593241 | 41593241 | 41593241 | 41593241