## PROJECT
COMMUNICATIONS MANAGEMENT PLAN
PROJECT DETAILS
PROJECT No: | MA-015-02
DATE: | 2021-12-11
FULL PROJECT NAME: | SIRBTC
PROJECT MANAGER: | Dyandra Paramitha Widyadhana
PROJECT SPONSOR:

## COMMUNICATIONS MANAGEMENT PLAN
COMMUNICATIONS MANAGEMENT PLAN
ID | STAKEHOLDER | INFORMATION | METHOD | TIMING OR FREQUENCY | SENDER | APPROVAL / SIGN OFF | ASSUMPTIONS | CONSTRAINTS
S001 | Project Sponsor Yulia Niza Zakiya Azizah Cahyaningtyas | Informasi mengenai update progress SDLC dan timeline | Melalui platform messaging app LINE setiap 3-4 minggu melalui Manajer Komunikasi | 3-4 minggu hingga waktu testing, 2 minggu sekali hingga closing. | Manajer Komunikasi Dyandra Paramitha | Manajer Waktu Akmal Zaki | - | Chat hanya pada hari kerja, jam 09:00-17:00
|  | Fitur, perubahan atau deliverables baru | Google Meet bersama team dan email | Setiap key milestones tercapai. | Manajer Komunikasi Dyandra Paramitha | Manajer Lingkup Akmal Zaki Manajer Biaya Daffa M. Azhar Manajer Pengadaan Kirana Zea M. | Diasumsi bahwa project sponsor sudah mengetahui topik dan menyetujui rapat | Menjadwalkan rapat 2 hari sebelum rencana pelaksanaan, menggunakan chat
S002 | Administrator Sistem Informasi RBTC | Manual fitur baru, manual sistem informasi untuk disebarkan ke pengguna sistem | Email | Waktu TBA (To Be Announced). | Manajer Komunikasi Dyandra Paramitha | Manajer Perubahan & Integrasi Kirana Zea M. | Diasumsi bahwa administrasi mengerti cara penggunaan web akan tetapi belum memahami cara menggunakan sistem administrasinya. | Ukuran file tidak lebih dari 25MB, format dalam bentuk pdf.
S003 | Dosen Teknik Informartika ITS | Pemberitahuan fitur baru untuk pengguna, dan survey untuk pelaksanaan | Email, dan pada website sistem informasi | Waktu TBA (To Be Announced). | Manajer Komunikasi Dyandra Paramitha | Manajer Perubahan & Integrasi Kirana Zea M. | Diasumsi bahwa produk sudah selesai dikembangkan dan sudah disetujui oleh Project Sponsor, informasi mengenai sistem dapat disebar. Diasumsi dosen sudah mengerti cara menggunakan website. | Melakukan komunikasi hanya pada hari kerja dan pada jam kerja Dosen.
S004 | Mahasiswa Teknik Informartika ITS | Pemberitahuan fitur baru untuk pengguna, dan survey untuk pelaksanaan | Message App LINE, email, dan pada website sistem informasi | Waktu TBA (To Be Announced). | Manajer Komunikasi Dyandra Paramitha | Manajer Perubahan & Integrasi Kirana Zea M. | Diasumsi bahwa produk sudah selesai dikembangkan dan sudah disetujui oleh Project Sponsor, informasi mengenai sistem dapat disebar. Diasumsi mahasiswa sudah mengerti cara menggunakan website. | -
| internal | myITS academy --> internal: orang yang kerja di dalam ITS, tp juga stakeholder

## CUSTOMISE
HOW TO CHANGE THE MENU ITEMS IN STATUS FIELDS
Default settings
We have not set any drop down menus, as it is likely that most projects will have different priorities and categories.
How to create a drop down menu
Click on Data tab > Data Validation > Settings > List
In the Source field enter the menu items separated by a comma.
To change the menu items
To change the menu options or remove the dropdown select Data > Data Validation > Settings > List
ADDITIONAL FIELDS YOU MIGHT WANT TO ADD
Actions - A column for any actions related to the communication or to manage an assumption.
Task ID/WBS ID - To record any associated tasks on the project schedule.
Risk ID - a look up to any associated risks.
Budget/costs estimate
Project ID - For large communications efforts you may have a separate project. For example there might be a project to translate comms into other languages.
Dependencies - Some comms may be dependent on other tasks being completed.
Approval/Sign-off - To record the person/group who has authority to approve the communication before it is sent.
This template was provided by
https://www.stakeholdermap.com/

## DEFINITIONS
DEFINITIONS
PROJECT MANAGER
The person with responsbility for managing and delivering the project. They will own this log, but may not be the person maintaining it.
PROJECT ID
The project number is assigned by the PMO (Project Management Office) once the project is approved for funding.
PROJECT SPONSOR
The person with ultimate accountablity for the project. They will hold the purse strings.
PROJECT TITLE
The name of the project, this should align with the name given on other project documents (rather than being a nickname).
STAKEHOLDER ID
Give each stakeholder a unique identifier or reference so that it can be easily traced.
STAKEHOLDER
Enter the name of the stakeholder or stakeholder group.
INFORMATION
Give as much detail as you can about the information that the stakeholder/group needs to receive. For example, 'High level information on go live, new features and training dates. '
METHOD
Describe how the information will be communicated. For example, email, meetings, website updates, events etc.
TIMING OR FREQUENCY
Describe when and how often the information will be communicated. For some stakeholders a regular update may be needed for others it may be a one off tied to an event. For example, notification of a new system going online with key technical information for a network support team.
SENDER
Give the person who will be responsible for making sure the communication is sent. This might not necessarily be the person who writes the email or delivers a presentation, but will be the person who makes the arrangements.
ASSUMPTIONS
Include any assumptions that you have made about the communication. For example that new website pages will be available or that assets for the comms will be ready e.g. a new logo. It is worth noting any assumptions you have made about the comms being successfully recieved. For example, it might be that you are assuming all users have email access. You might also be assuming that spam filters will not be a problem. Or you may assume that all recipients can read English to a particular level.
CONSTRAINTS
Enter any factors that constrain the communication. For example, a date by which it must be delivered, or a max file size for email.
This template was provided by
https://www.stakeholdermap.com/